## Goal 2 Health PS
TOKELAU EDUCATION STRATEGIC PLAN 2020 - 2025
STRENGTHENED HEALTH AND WELL BEING FOR LEARNING
Strategic Goal 2 | Raise a healthier, safer, and well generations of young people that contribute to resilient and sustainable communities | [5 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
Outcome 1 |  |  | Who | When | Cost min | Cost max | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Support school communities to improve child and youth well being for learning through adopting the Health Promoting Schools initiative | 1.1 | Form partnerhips initially betweend Education and Health to engage with schools and their communities to establish HPS as a key initiative in meeting both education and health goals;
|  | 1.1.1 DOE complete a planned process of preparations before engaging with Health: a) Appoint the HPS Coordinator; b) Prepare presentations on - What is HPS, Purpose, Intended Outcomes, Impact, HPS Inquiry Cycle, Health audit, Self-review rubric, 3-4 year time frame, resourcing, roles and responsibilities, HPS Guidelines | GoT DOE | Q3 2020
|  | 1.1.2 Health and Education initial one week, and ongoing, engagement to co-construct a common plan, baseline data and measures, and working collaboratively | GoT, DOE/DOH | Q4 2020
|  | 1.1.3 Health, Education engagement with each school community about HPS; form partnerships with and between the school community, Health, Education and other sectors to engage with schools and establish HPS as a important intiative for health and well being for learning | GoT, DOE/DOH | Q2 2021
|  | 1.1.4 Create an active small group HPS Task Force in the school leading and coordinating HPS actions led by a school HPS liaison person and include non teaching staff, teachers, students, principal, community member | GoT DOE | Q4 2020
|  | 1.1.5 Provide and sustain capacity building of key HPS personnel across sectors | GoT, DOE/DOH | Q4 2020 and ongoing
|  | 1.1.6 HPS work with the school community to scope the health and wellbeing in their school, to look at their own practices and conduct an audit of their health promoting actions according to WHO 6 elements for Health Promotion | GoT, DOE/DOH | Q2,3, 2021
|  | 1.1.7 HPS support schools to complete a self review using the HPS health and well being for learning self review tool | GoT | Q2,3, 2021
|  | 1.1.8 HPS support school community to collectively identify health and well-being priorities that are hindering children and young people from achieving outcomes | GoT DOE | Q2,3, 2021
|  | 1.1.9 HPS support school partners to co-construct the plan, identifying strategies most likely to address the health/wellbeing priorities; and determine measures of success. The strategies build on the school community's strengths. | GoT DOE | Q2-4, 2021
|  | 1.1.10 Through collaborative partnerships, the school community puts in place school-wide actions that are then monitored, reviewed and evaluated as part of the school’s strategic and annual planning targets. Support is differentiated to build on the school community’s capability and capacity | GoT, DOE/DOH | Q1 2022 ongoing
|  | 1.1.11 HPS support schools conduct an evaluation on the actions and outcomes, describing the changes in thinking and practice through critical reflection on the evidence. The evaluation methodology tracks ongoing progress and determines if the strategy has been successful and why. | GoT, DOE/DOH | Twice yearly mid and end of year reviews
|  | 1.1.12 HPS with the school report evaluation results to the school community partnerships, who confirm the next steps and the beginning of a new cycle. | GoT, DOE/DOH | Q4 yearly
Outcome 2 |  |  | Who | When | Cost min | Cost max | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Support schools to improve child and youth well being through improving the nutritional quality of their diet and promotion of healthy and sustainable food habits | 2.1 | Establish and sustain school canteens in each of the three schools
|  | 2.1.1 HPS support schools to inquire into the nutritional quality of student's diet | GoT, DOE/DOH | Q1 2021
|  | 2.1.2 Schools to scope their community's support for a school canteen | GoT, DOE/DOH | Q1 2021
|  | 2.1.3 HPS to support school community partnerships to develop specifications for a school canteen, action plan, determine measures of success, explore and cost options for the physical space, operations, and sustainability; confirm sources of funding; present options to the Education Committee and Taupulega for consideration, approval; Implement the action plan | GoT, DOE/DOH | Q2 2021
|  | 2.1.4 HPS and school community partners co-construct a school nutrition and drinks policy; promote healthy and sustainable food habits | GoT, DOE/DOH | Q3 2021
|  | 2.1.5 Appoint a canteen operator | GoT, DOE/DOH | Q3 2021
|  | 2.1.6 Design and trial a canteen menu that is aligned to the policy, submit proposed menu options for the HPS Task Force approval | GoT, DOE/DOH | Q3 2021
|  | 2.1.7 Evaluate, reflect and review | GoT, DOE/DOH | Q4 2021
Outcome 3 |  |  | Who | When | Cost min | Cost max | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Support schools to revive school gardens to promote important life skills around sustainable food habits | 3.1 | Establish and maintain a thriving school garden
|  | 3.1.1 DOE to form partnerships with EDNRE and other relevant parties on island, develop and present proposal for a school garden for Taupulega support | GoT DOE/EDNRE | Q3 2021
|  | 3.1.2 HPS Task Force, school community to review the current or previous practices around school gardens, establish factors important for sustaining school garden efforts; | GoT DOE/EDNRE | Q4 2021
|  | 3.1.3 Draw up specification for a school garden, with costed options; complete and implement an action plan to revive, establish and sustain a school garden, enlisting volunteers and hiring as funds allow | GoT DOE/EDNRE | Q1 2022
|  | 3.1.4 Develop and implement a Grow, Harvest, Prepare and Share programme using the produce from the school garden, that also links to the School Canteen | GoT DOE/EDNRE | Q4 2022
|  | 3.1.5 5. Evaluate, reflect, review, share and celebrate | GoT DOE/EDNRE | Q4 yearly
Outcome 4 |  |  | Who | When | Cost min | Cost max | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Design and publish Health and Physical Education (HPE) and Wellbeing curriculum, and curriculum resources | 4.1 | Develop, produce and implement the Health PE and Wellbeing Curriculum for Tokelau schools
|  | 4.1.1 DOE and Health partnership develop agreed processes and curriculum committee for drafting, reviewing and rewriting, publication | GoT DOE/HEALTH | Q3 2020
|  | 4.1.1 Develop Terms of Reference for a technnical support person to produce a draft curriculum statement for consultation, and produce the final version in response to feedback | GoT DOE/HEALTH | Q3 2020
|  | 4.1.2 Confirm funding, recruit and appoint technical support | GoT DOE/external support | Q4 2020
|  | 4.1.3 Technical support and curriculum committee agree on an action plan and timeframes | GoT DOE Consultant | Q4 2020
|  | 4.1.4 Develop review and publish the curriculum statement | Consultant | Q1-2 2021
|  | 4.1.5 Develop and produce modules of learning to support teachers' understanding to implement the curriculum | Consultant | Q1-2 2021
|  | 4.1.6 Implement in-service training to implement the curriculum | DOE/ Consultant | Q1 2022, ongoing for the year DOE
Outcome 5 |  |  | Who | When | Cost min | Cost max | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Promote more inclusive and sustainable growth through developing and implementing social protection systems for children and students with disabilities | 5.1 | Develop, produce and implement policies and strategies for the Social Protection of children and students with disabilities
5.1.1 Design and implement a situational analysis for people with disabilities in Tokelau
5.1.2 Provide technical support to carry out diagnostic assessments of students with disabilities
5.1.3 Develop policy and strategies to increase social protection for students with disabilities
5.1.4 Implement strategies, monitor and evaluate the situation for students with disabilities